## PLANNING
WEEK | TASK ID | TASK | EXTRA INFO | FINSHED DATE | Status | Duplicates
WEEK 1-2
Was a combined week beacuse I was not at stage | 1 | Mentor beter overzicht geven alle informatie | - | - | ok
| 2 | Meer begrip krijgen in blockhain | - | - | ok
| 3 | Simple blockhain aplicatie maken om beter me kunnen omgaan. | - | - | ok
| 4 | Predict what the documents should have | Learn more about the documents | - | ok
| 5 | Onderdelen die ik niet begrijp, noteren en bijleren als tijd over is | - | - | ok
WEEK 3
| 7 | Gather information about what we want to put on a bench mark | fps, load, esc | 2025-02-20 | Done
| 8 | Create a desing for the bench mark | text base and Grah | 2025-02-21 | Done
| 9 | create mocup api for benchmark data | test api | 2025-02-22 | Done
| 10 | find out what you need to do to use WebGPU in every platform | android, windows 11, mac - google.. | 2025-02-22 | Done
Week 4
| 11 | Gather most important information about game pad imputs in HTML 5 | GamePad imputs handy to have | 2025-02-24 | Done
| 12 | Make a ui for a game benchmark for a gamepad | GamePad imputs | 2025-02-25 | Done
| 13 | Make a mocup api for benchmarking gamepad | Gamepad test Api | 2025-02-24 | Done
| 14 | Shaders-documentation | Shaders info | 2025-02-25 | Done
Week 5
| 15 | Gather most important nextwork statistics for the player | doc, network | 2025-03-04 | Done
| 16 | Make a ui for the network statistics | network | 2025-03-04 | Done
| 17 | create mocup api for network data | network | 2025-03-04 | Done
| 18 | Work on prototype in tetra-mini | How to get: WebGPU, Gamepad, Network | - | Unfinshed
| 19 | Write a document for school | doc, reacherge bundel | - | Unfinshed
week 6
| 19 | Write a document for school | doc, reacherge bundel | 2025-03-12 | Done | 2
| 18 | Work on prototype in tetra-mini | How to get: WebGPU, Gamepad, Network | 2025-03-13 | Done | 2
week 7
| 20 | Text Frontend Template | TASK 0: Project | 2025-03-18 | Done
| 21 | Dom injection from browser extention | TASK 0: Project | 2025-03-19 | Done
| 22 | Comuncation between ui and extention | TASK 0: Project | 2025-03-20 | Done
| 23 | Gather: Machine information | TASK 0: Project | - | Unfinshed
week 8
| 23 | Gather: Machine information | TASK 0: Project | 2025-03-24 | Done | 2
| 24 | Gather: Render infromation | TASK 0: Project | 2025-03-24 | Done
| 25 | Gather: Shader information | TASK 0: Project | 2025-03-25 | Done
| 26 | Gather: Memory information | TASK 0: Project | 2025-03-25 | Done
| 27 | Gather: Networkinformation | TASK 0: Project | 2025-03-26 | Done
| 28 | Clean up Gathering code | TASK 0: Project | 2025-03-26 | Done
| 29 | better iframe movment and scaling | TASK 0: Project | 2025-03-27 | Done
| 30 | extention menu settings: hide different type of values, trasparancy | TASK 0: Project | - | Unfinshed
Week 9
| 30 | extention menu settings: hide different type of values, trasparancy | TASK 0: Project | 2025-04-07 | Done | 2
| 31 | Add functionalty to the menu that interacts with backend and Iframe | TASK 0: Project | 2025-04-09 | Done
| 32 | Gamepad UI | TASK 0: Project | 2025-04-11 | Done
Week 10
| 36 | Test Result Document Writing | Cant finsh, dusnt have all of the test | - | Unfinshed
| 37 | Research Results/Findings Document Writing | Big Task - Will take more weeks to finsh | - | Unfinshed
Week 11
| 37 | Research Results/Findings Document Writing | Big Task - Will take more weeks to finsh | - | Unfinshed | 2
| 38 | Better ui/handeling with the extention | extention was anoing | 2025-04-25 | Done
Week 12
| 37 | Research Results/Findings Document Writing | Big Task - Will take more weeks to finsh | - | Unfinshed | 3
| 40 | Controler implementation | Replace Moc data with a acutal controler | - | Busy
Week 13
| 40 | Controler implementation | Replace Moc data with a acutal controler | - | Done | 2
| 36 | Test Result Document Writing | Cant finsh, dusnt have all of the test | - | Unfinshed | 2
Week 14
| 36 | Test Result Document Writing | Cant finsh, dusnt have all of the test | - | Done | 3
| 37 | Research Results/Findings Document Writing | Big Task - Will take more weeks to finsh | - | Busy | 4

## TASKBOARD
TASK ID | TASK | EXTRA INFO
1 | Mentor beter overzicht geven alle informatie |  | https://trello.com/b/rbikyZPc/tetra-performance-suite
2 | Meer begrip krijgen in blockhain |  | Opgelet: dit staat helemaal los van het testplan en de testresultaten, die moeten ook ingeleverd worden bij een onderzoekstage!
3 | Simple blockhain aplicatie maken om beter me kunnen omgaan.
4 | Predict what the documents should have | Learn more about the documents
5 | Onderdelen die ik niet begrijp, noteren en bijleren als tijd over is
6 | Get some info about what i acctualy have to do | im in a meating and get information
7 | Gather information about what we want to put on a bench mark | fps, load, esc
8 | Create a desing for the bench mark | text base and Grah
9 | create mocup api for benchmark data | test api
11 | Gather most important information about game pad imputs in HTML 5 | GamePad imputs handy to have
12 | Make a ui for a game benchmark for a gamepad | GamePad imputs
13 | Make a mocup api for benchmarking gamepad | Gamepad test Api
14 | Shaders-documentation | Shaders info
15 | Gather most important nextwork statistics for the player | doc, network
16 | Make a ui for the network statistics | network
17 | create mocup api for network data | network
18 | Work on prototype in tetra-mini | How to get: WebGPU, Gamepad, Network
19 | Write a document for school | doc, reacherge bundel
20 | Text Frontend Template | TASK 0: Project
21 | Dom injection from browser extention | TASK 0: Project
22 | Comuncation between ui and extention | TASK 0: Project
23 | Gather: Machine information | TASK 0: Project
24 | Gather: Render infromation | TASK 0: Project
25 | Gather: Shader information | TASK 0: Project
26 | Gather: Memory information | TASK 0: Project
27 | Gather: Networkinformation | TASK 0: Project
28 | Clean up Gathering code | TASK 0: Project
29 | better iframe movment and scaling | TASK 0: Project
30 | extention menu settings: hide different type of values, trasparancy | TASK 0: Project
31 | Add functionalty to the menu that interacts with backend and Iframe | TASK 0: Project
32 | Gamepad UI | TASK 0: Project
33 | Gamepad selection | TASK 0: Project - Fake data
34 | Gamepad information show up correctly | TASK 0: Project - Fake data
35 | Joystick movment corrections | TASK 0: Project - Fake data
36 | Test Result Document Writing | Cant finsh, dusnt have all of the test
37 | Research Results/Findings Document Writing | Big Task - Will take more weeks to finsh
38 | Better ui/handeling with the extention | extention was anoing
39 | Bug fixing | Fix some issues in rare casses
40 | Controler implementation | Replace Moc data with a acutal controler

## WeeklyRaport
WEEK 1
Ik heb eigelijk en korte test hier op gehad met sam en andere leden van AZTEQ waar ik een korte presentatie moest doen